## Sheet1
Apprenticeship On-Boarding Planning Tool | Employer: | INSERT
Activity WC: | 2021-01-01 | 2021-01-08 | 2021-01-15 | 2021-01-22 | 2021-01-29 | 2021-02-05 | 2021-02-12 | 2021-02-19 | 2021-02-26 | 2021-03-05 | 2021-03-12 | 2021-03-19 | 2021-03-26 | 2021-04-02
Information Advice & Guidance from Employer Partnership Manager | 2021-01-01: Note key Holiday periods and extend time accordingly.
Head of Business Engagement: P.clarke@shu.ac.uk
Apprentice complete online application and provides certificates of existing qualifications | 2021-01-01: Application
Contact: apprenticeships@shu.ac.uk (Operations Team)
Conditional Offers Made (including instructions for Comitment Statement) | 2021-01-15: Conditional Offers
Apprenticeship Operations Team / Partmerships & Contracts Team / Admissions
Initial Assessment - BKSB Completed by Apprentice | 2021-01-29: Initial Assessment
Contact: apprenticeships@shu.ac.uk (Operations Team)
Skills Scans completed by Apprentice with Employer | 2021-01-29: Skills Scan
Apprenticeship Impact & Information Resource - Employer Commitment
Employer mentors engage in Training Plan Toolkit | 2021-01-29: Training Plans
Apprenticeship Impact & Information Resource - Employer Commitment
Suitability Discussions bewtween WBL Coach, employer and Apprentice | 2021-02-12: Suitability Discussion
Work Based Learning Team - Specific Work Based Learning Coach contact
Commitment Statement & Apprenticeship Agreement released and returned | 2021-02-26: Commitment Statement
Contact: apprenticeships@shu.ac.uk (Operations Team)
Final Checks for Offer Conditions and Enrolment Check | 2021-02-26: Invitations released; 2021-03-19: Enrolment Check
Partnership and Contracts Team
Attendance at Welcome Event including Mentor Training | 2021-02-26: Invitations released; 2021-03-26: Mentor Event
Head of Work Based Learning s.moorwood@shu.ac.uk
Framework Agreement / Contract for Services (Signed and returned) | 2021-01-08: Contracts
Partnership and Contracts Team
Course Start Date, including induction (specify if Mentors involved) Arrange first APR | 2021-02-26: Timetable released; 2021-04-02: Start
Academic Course Leader